## Bug Tracker
Bug ID | Date Reported | Reported By | App Area | Module | Bug Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Assigned To | Target Fix Date | Date Fixed | Retest Date | Retest Result | Root Cause | Fix Notes | Related Test Case ID | Evidence Link | Comments | Age (Days)
BUG-001 | 2026-06-07 | UAT Tester | Customer App | Vehicle Management | The same vehicle can be registered multiple times | Log in, go to the garge and register a vehicle. register the same vehicle a second time | The same vehicle should not be registered multiple times | Duplicate registeration of a vehicle is suceessful | Major | High | New |  | 2026-06-12 | [5 empty] | VEH-05
BUG-002 | 2026-06-07 | UAT Tester | Customer App | Booking | Booking time slot does not captures all timeslot including the seasonal ones | Open booking and enter all the required fields, on the booking time field select one of the various time slots that is most sutable | Time slot selected | The available time slots does not cover all the time slots that a customer can pick | Critical | Critical | New |  | 2026-06-12 |  |  |  |  | Use the Seasional sessions table for details of timeslots | ADM-VEN-01
BUG-003 | 2026-06-08 | UAT Tester | Customer App | Booking | No service phone no field | Open booking and while entering the required details for the booking, there is no phone no captured for the booking | Service phone no shoud be captured | No field to enter Phone no | Critical | Critical | New |  | 2026-06-12 | [5 empty] | BOOK-01
BUG-004 | 2026-06-08 | UAT Tester | Customer App | Cancellation | Cancellation policy document not included | Open bookings to view list of bookings, select the booking to cancel and click on cnacel | Cancellation pop up should show with a link to the full cancellation policy | Cancellation pop up shows, but there is no link to cancellation policy | Major | High | New |  | 2026-06-12 |  |  |  |  | Cancellation policy doc will be provided | CAN-01
BUG-005 | 2026-06-08 | UAT Tester | Customer App | Booking | Service address field cannot be verified | Open booking and enter all the required fields, on theservice address field enter any address arbitary value | Service address provided should be a UK(Aberdeen, Scotland precisely) address | User can enter any value and the system accepts it | Critical | High | New |  | 2026-06-12 |  |  |  |  | Use the Postcode Address Lookup API for address verification. Doc will be provided | BOOK-01
BUG-006 | 2026-06-08 | UAT Tester | Customer App | Error Handling | Session does not timeout after hours away | Log in to app and leave app for more than 10 min | Session shoukd timeout sfter begin away from app after some time | Session remains active even after hours of inactivity | Critical | Critical | New |  | 2026-06-12 | [5 empty] | ERR-CUS-12
BUG-007 | 2026-06-08 | UAT Tester | Customer App | Error Handling | Sign in page does not allow user toggle password on and off | Go to login page and enter email and password. The user cannot view the password he/she is entering | User should be able to toggle on or off the password field to view password being enteed | User cannot see the password being entered | Minor | Medium | New |  | 2026-06-12 | [5 empty] | ERR-CUS-01 |  |  | 7
BUG-008 | 2026-06-08 | UAT Tester | Customer App | Error Handling | Error message during network failure | [16 empty] | 7
BUG-009 | 2026-06-12 | UAT Tester | Both | Promotions | Discrepancy with the discount calculations | Created a 10% discount promotion for first time sign-ups in the Admin app and applied to all users. In the user app book a wash, at review booking you would notice a miscalulation to total | 10% discount on the mini-valet service(only) should bring the total to the mini-valet cost -10% | A total of more that 10% was deducted from the mini-valet service(Total for standard wash should have been 22.5 but i got 19.85) | Critical | Critical | New |  | 2026-06-17 | [5 empty] | PRO-CUS-03 |  |  | 3
BUG-010 | 2026-06-15 | UAT Tester | Admin App | Dashboard | Total Renenue does not compute | Book a wash on the customer app. Log in to admin app, on the dashboard, the tota revenue does not compute | Total revenue after all bookings should be visible on the dash board | Totla revenue remains at 0.00 | Critical | Critical | New |  | 2026-06-20 | [8 empty] | 0
BUG-011 | 2026-06-15 | UAT Tester | Admin App | Admin Authentication | Admin user session foes not expire after extended periods | Log in to the admin portal and leave the account logged in for extended periods | Admin user should be logged out after a specified period | User remains logged in even after 24 hours | Major | High | New |  | 2026-06-20 | [5 empty] | ADM-AUTH-04 |  |  | 0
Formulas:
Age (Days) = IF([Date Reported]="","",TODAY()-[Date Reported])

## Dashboard
NEXA UAT Bug Tracker Dashboard
Metric | Value | Notes
Total Bugs | 11 | All logged bugs
Open Bugs | 11 | Anything not fixed/closed
Fixed Bugs | 0 | Ready for closure or release note
Closed Bugs | 0 | Verified and closed
Critical / High Priority | 9 | Needs urgent action
Overdue Open Bugs | 7 | Target fix date has passed
Status | Count |  | Priority | Count | App Area | Count
New | 10 |  | Critical | 5 | Customer App | 8
Triaged | 0 |  | High | 4 | Admin App | 2
In Progress | 0 |  | Medium | 1 | Both | 1
Ready for Retest | 0 |  | Low | 0
Retesting | 0
Fixed | 0
Closed | 0
Rejected | 0
Duplicate | 0

## Lists
Status | Priority | Severity | App Area | Module | Environment
New | Critical | Blocker | Customer App | Authentication | UAT
Triaged | High | Critical | Customer App | Vehicle Management | Staging
In Progress | Medium | Major | Customer App | Booking | Production
Ready for Retest | Low | Minor | Customer App | Payment | Development
Retesting |  | Cosmetic | Customer App | Cancellation
Fixed |  |  | Customer App | Review
Closed |  |  | Admin App | Admin Authentication
Rejected |  |  | Admin App | Booking Management
Duplicate |  |  | Admin App | Vendor Assignment
|  |  | Admin App | Payment & Refund
|  |  | Admin App | Error Handling
|  |  | Both | Notifications
|  |  | Both | Security / Access Control
Promotions
Dashboard

## How to Use
How to Use the NEXA UAT Bug Tracker
Step | Instruction
1 | Log every defect on the Bug Tracker sheet using one row per bug.
2 | Use the Bug ID format BUG-001, BUG-002, etc.
3 | Set Severity based on user/business impact and Priority based on fix urgency.
4 | Update Status as the bug moves from New → Triaged → In Progress → Ready for Retest → Fixed → Closed.
5 | Add the related UAT test case ID, such as AUTH-01 or ADM-PAY-04, for traceability.
6 | Use Evidence Link for screenshots, screen recordings, logs, or ticket links.
7 | Dashboard updates automatically from the Bug Tracker sheet.